## Sheet1
	Entry	Tasks	Exit	Who	Notes
Initiation	IT Service Request		Existence of Conceptual proposal	- Customer / - Intake Authority (IA) / - IT technical assessor	Make sure that / - reasonable solution can be built. / - No legal problems arise / - Solution does not already exist or is / already being developed

Planning / (Requirement Analysis)		- Address deficiencies / - Propose improvements / - Plan basic project approach / - Conduct feasibility study / - economic / - operational / - techical / - Quality requirement analysis / - Risk identification / - Project management plan / - Schedule, Milestones / - Acquisition of resources / - Breakdown of tasks / - Define scope boundary!	Approvement of / - Budget / - Proj. Mgmt plan / - Project charter	- Senior Members / - Sponsor / - Project manager / - Stake holders / - Domain experts	Most important and fundamental stage

Defining / (Analysis)		- Create SRS		- Project manager / - Business analyst / - Subject matter expert / - Designer / - Test leads	SRS (Software Requirement Sepcification) consists of all the product requirements to be designed and developed during the project life cycle.

Designing		- Create DDS / - Hardware / - OS / - Programmin languages / - Security / - Data (interfaces, flow) / - Stakeholders to review DDS / - risks / - robustness / - modularity / - budget / - time		- Customers / - End users / - Project manager / - Business analyst / - Technical architect / - Developers / - Database (DBA)	DDS: Design Document Specification

Building / (Construction)		- Start development / - Build software / - Train users		- Developers / - DBAs / - Project Managers	Follow coding guidelines

Testing / (Integration / Functional evaluation)		Defects to be / - reported / - tracked / - fixed / - retested / Repeat until quality reached.		- Project Manager / - Developers / - DBAs / - Implementation manager / - Integration manager

Deployment		Identify deficiencies and start cycle again